## Slide 1
Communications System
Integration Status Review (ISR)
5/5
Comms Layers
Complete
✓
IF-6 (Drone↔Drone)
Verified
0%
Packet Loss
Complete
<5ms
RTT Latency
Complete
Notes: TALKING POINTS: - Distributed swarm coordination for 20-50 autonomous surface drones - ESP32-S3 with ESP-NOW protocol — zero-configuration networking - All 5 communication layers complete and verified on hardware - Interface IF-6 (drone-to-drone) fully verified — 0% packet loss, sub-5ms RTT - Integration Phase 0 (interface specs) starting this week TIME: 30 seconds

## Slide 2
Hardware Architecture & Status
ESP32-S3 Communication Hardware
THE UNIVERSITY OF ARIZONA
2
AQUABOTS | ISR – Communications System
ESP32-S3 Specifications
MCU: Xtensa Dual-Core @ 240 MHz
Radio: 2.4 GHz WiFi (ESP-NOW)
Protocol: ESP-NOW (up to 250 kbps)
Antenna: On-board PCB antenna
Range: 30m+ indoor, 100m+ outdoor
Power: 3.3V from distribution board
UART: 0=Console, 1=Pixhawk, 2=Jetson
Hardware Status
MCU selected & tested (ESP32-S3)
2-node communication verified
RSSI: -16 to -24 dBm at 1m
Multi-node setup (Phase 1, Wk 8)
Waterproof enclosure (Phase 3, Wk 12-13)
Timeline: Wk 8 → 3rd board + stub tests | Wk 10 → Pair tests | Wk 12 → Full system
Notes: TALKING POINTS: - ESP32-S3 selected for dual-core processing, built-in 2.4GHz WiFi - ESP-NOW eliminates need for WiFi access point — direct peer-to-peer - Currently verified on 2 development boards - UART port allocation planned: UART0=console, UART1=Pixhawk (IF-1), UART2=Jetson (IF-3) - 3rd dev board arriving Week 8 for multi-node and stub testing - Waterproof enclosure integration during Phase 3 full system testing TIME: 45 seconds

## Slide 3
Software Stack – Layers 1-5
All 5 communication layers complete and verified on hardware
THE UNIVERSITY OF ARIZONA
3
AQUABOTS | ISR – Communications System
5
Layer 5: Commands
GOTO, HOLD, STOP, RESUME — synchronized execution
✓
4
Layer 4: Coordination
Leader election (highest ID) + TDMA scheduling (50ms slots)
✓
3
Layer 3: Discovery
HELLO/JOIN auto-discovery — 2-4 sec, 50-node capacity
✓
2
Layer 2: Identity
NVS provisioning — persistent node IDs (1-254)
✓
1
Layer 1: Transport
ESP-NOW wrapper — 4-5ms RTT, 0% packet loss
✓
Key Metrics
~2,350
Lines of Code
5 of 5
Modules
~10 KB
RAM Usage
~800 KB
Flash Usage
<5%
CPU Load
6 weeks
Dev Time
Notes: TALKING POINTS: - All 5 communication layers complete — this is the full swarm comm stack - Layer 1: ESP-NOW wrapper handles all radio communication - Layer 2: Each drone gets a persistent unique ID via NVS flash - Layer 3: Drones discover each other automatically — zero-config - Layer 4: Highest ID drone becomes leader, generates TDMA schedule - Layer 5: Leader distributes GOTO/HOLD/STOP/RESUME commands - ~2,350 lines production-quality C code in ESP-IDF - Very lightweight: <5% CPU, ~10KB RAM - Note: These 5 layers implement IF-6 (drone↔drone) which is fully complete TIME: 60 seconds

## Slide 4
SRVM Verification – Requirement 4.4.2
Inter-Drone Communication: PARTIAL PASS → Advancing to FULL PASS
THE UNIVERSITY OF ARIZONA
4
AQUABOTS | ISR – Communications System
Verification Method | Status | Evidence / Detail | Date
TEST | ✓ PASS | RTT <5ms ¦ 0% loss ¦ RSSI -16 to -24 dBm ¦ Discovery <5s | Wk 6
DEMONSTRATION | ✓ PASS | 2-node swarm: auto-discovery, leader election, TDMA, cmd sync | Wk 6
ANALYSIS | ◐ In Progress | Scalability 2→50 nodes, traffic modeling, performance projections | Wk 9
INSPECTION | ○ Planned | Hardware inspection, antenna placement, enclosure RF check | Wk 12
Supporting Requirements
4.1.2 Swarm Control — Demonstration: ✓ PASS (leader election, synchronized commands)
4.4.1 Autonomy & Control — Demonstration: ◐ PARTIAL (command execution OK, formation pending)
4.3.1 Survivability — Test: ✓ PASS (0% packet loss) | Analysis: Scheduled Wk 9
Notes: TALKING POINTS: - Requirement 4.4.2 currently at PARTIAL PASS, advancing to FULL PASS - TEST: All metrics exceed requirements — RTT <5ms, 0% packet loss, excellent signal - DEMONSTRATION: Full 2-node swarm demonstrated — discovery through command execution - ANALYSIS: Scalability study scheduled during Spring Break buffer (Wk 9) - INSPECTION: Hardware inspection during Phase 3 full system integration (Wk 12) - Supporting requirements also on track TIME: 60 seconds

## Slide 5
Live Demonstration
2-Node Swarm Communication — End-to-End Verification
THE UNIVERSITY OF ARIZONA
5
AQUABOTS | ISR – Communications System
1
Power On
Two ESP32-S3 boards powered up
2
Auto-Discovery
Nodes discover each other (2-4 sec)
3
Leader Election
Node 2 (highest ID) elected leader
4
TDMA Schedule
Leader generates 50ms time slots
5
Send Command
Leader sends: goto 100 200 90
6
Synchronized Exec
Both nodes receive & execute
Backup: Pre-recorded video + console screenshots available if live demo encounters issues
Notes: TALKING POINTS: - Live demo: Watch two ESP32-S3 boards coordinate in real-time - Power on → automatic discovery in 2-4 seconds - Node 2 becomes leader (highest ID wins) - Leader generates TDMA schedule — 50ms slots prevent collisions - Leader sends GOTO command — both nodes receive and execute - Console shows synchronized status on both boards - Backup video ready if hardware has issues TIME: 2 minutes for demo

## Slide 6
Software Integration Plan
5 Phases (0-4) — Integration-Maturity Model with Team Pairings
THE UNIVERSITY OF ARIZONA
6
AQUABOTS | ISR – Communications System
Phase 0: Interface Agreement
5 interface specs (IF-1 to IF-5); team sign-off by Feb 28
Wk 7
IN PROGRESS
Phase 1: Pairwise Stub Testing
Each IF tested: one real side + one stub; Spring Break buffer Wk 9
Wk 8-9
Upcoming
Phase 2: Subsystem Pair Integration
Real HW connected in pairs — Swarm↔Pixhawk, Sensors↔ESP32, GUI↔Jetson
Wk 10-11
Planned
Phase 3: Full System Integration
All 4 subsystems running on complete drone; 2-drone swarm; E-STOP
Wk 12-13
Planned
Phase 4: Pool Testing & Validation
Single-drone pool → multi-drone pool → full mission test
Wk 14-15
Planned
John's IF Ownership
IF-1: Swarm ↔ Pixhawk (w/ Robert)
IF-2: Sensors → ESP32 (w/ Jamie)
IF-3: ESP32 ↔ Jetson (w/ Jamie)
IF-5: GUI Cmds → Drone (w/ Mayra)
IF-6: Drone ↔ Drone ✓ DONE
Critical Path
IF-1: Swarm ↔ Pixhawk
Two MCUs, two owners, real-time protocol
Tested earliest; most schedule buffer
MAVLink over UART — spec due Feb 26
Notes: TALKING POINTS: - Integration plan follows 5 phases (0-4) based on integration maturity, NOT subsystem breakdown - Phase 0 (THIS WEEK): All 4 team members agree on interface specs — IF-1 through IF-5 - IF-6 (drone↔drone ESP-NOW) already complete and verified - Phase 1 (Wk 8-9): Stub testing — each interface tested with one real side + one mock - Spring Break (Wk 9) used as buffer - Phase 2 (Wk 10-11): Real hardware pairs connected — Swarm↔Pixhawk is first (critical path) - Phase 3 (Wk 12-13): Full system on complete drone, 2-drone swarm, E-STOP - Phase 4 (Wk 14-15): Pool testing — single then multi-drone - CRITICAL PATH: IF-1 (Swarm↔Pixhawk) — two MCUs, two team members, real-time MAVLink - Must be tested earliest with most schedule buffer - I own or co-own 5 of 6 interfaces (IF-1, 2, 3, 5, 6) TIME: 60 seconds

## Slide 7
Testing & Validation Results
Verified Performance Metrics — Requirement 4.4.2
THE UNIVERSITY OF ARIZONA
7
AQUABOTS | ISR – Communications System
RTT Latency
4-5 ms
Req: <10 ms
PASS
Packet Loss
0%
Req: <5%
PASS
Signal Strength
-16 to -24 dBm
Req: >-70 dBm
PASS
Discovery Time
2-4 sec
Req: <5 sec
PASS
Functional Verification Results
Test Case | Result | Detail
Auto-Discovery (2 nodes) | ✓ PASS | Both nodes discovered in 2-4 seconds
Leader Election | ✓ PASS | Highest node_id (Node 2) elected correctly
TDMA Scheduling | ✓ PASS | 50ms slots generated, beacon every 1s
Command Distribution | ✓ PASS | GOTO/HOLD/STOP/RESUME — <50ms latency
Leader Failover | ✓ PASS | Auto re-election in 5-7 sec after power-off
Thread Safety | ✓ PASS | Mutex protection, zero race conditions
Notes: TALKING POINTS: - All performance metrics EXCEED requirements - RTT 4-5ms against <10ms plan requirement — well within threshold - Packet loss is 0% — well below 5% requirement - Signal strength -16 to -24 dBm — far exceeds -70 dBm minimum - Discovery in 2-4 seconds — well under 5 second requirement - All functional tests pass: discovery, election, scheduling, commands, failover - Thread safety verified — no race conditions with mutex protection - These metrics verified per Integration Plan Section 6.1 TIME: 45 seconds

## Slide 8
Master Integration Timeline
Integration Schedule and Key Milestones
THE UNIVERSITY OF ARIZONA
8
AQUABOTS | ISR – Communications System
7
8
9
10
11
12
13
14
15
16
17
Wk
NOW
BREAK
Ph 0: IF Specs
Ph 1: Stub Testing
Ph 2a: Swarm↔Pixhawk
Ph 2a: Sensors↔ESP32
Ph 2b: E2E Command
Ph 3a: Full Stack
Ph 3b: 2-Drone Swarm
Ph 4: Pool Testing
Finalize + Submit
In Progress
John's Tasks
Critical Path (IF-1)
Pair/System Tests
Notes: TALKING POINTS: - Timeline matches Software Integration Plan Master Timeline (Section 10) - Week 7 (NOW): Phase 0 — finalizing interface spec documents with all teammates - IF1_SPEC.md (John+Robert), IF2_SPEC.md (Jamie+John), IF3_SPEC.md (John+Jamie) - IF5_SPEC.md (Mayra+John) — team sign-off meeting Feb 28 - Week 8: Phase 1 — pairwise stub testing — each interface one real side + one stub - Week 9: Spring Break — buffer for async catch-up - Week 10: Phase 2a — CRITICAL: Swarm↔Pixhawk pair test (John+Robert) - ESP32 goto → Pixhawk motor spins, rudder deflects, ACK received - Week 11: Phase 2b — End-to-end command chain: GUI→MQTT→Jetson→ESP32→Pixhawk - Weeks 12-13: Phase 3 — Full system on drone, then 2-drone swarm + E-STOP - Weeks 14-15: Phase 4 — Pool testing (single then multi-drone) - Weeks 16-17: Finalize documentation and submit TIME: 45 seconds

## Slide 9
Next 30 / 60 / 90 Day Plan
Milestones, Deliverables, and Integration Targets Through May
THE UNIVERSITY OF ARIZONA
10
AQUABOTS | ISR – Communications System
30 Days
Feb 24 – Mar 27
Wk 7: IF-1, IF-2, IF-3, IF-5 specs agreed
Wk 7: Team sign-off meeting (Feb 28)
Wk 8: ESP32 sends MAVLink GOTO/STOP (1.1)
Wk 8: ESP32 reads sensor structs (1.4)
Wk 8: ESP32↔Jetson serial packets (1.8)
Wk 9: Spring Break buffer / catch-up
Wk 10: Swarm↔Pixhawk pair test (2.1)
Wk 10: Live sensor flow into ESP32 (2.2)
Wk 11: E2E cmd: GUI→ESP32→Pixhawk (2.4)
Wk 11: 2-drone swarm + Pixhawk (2.5)
60 Days
Mar 27 – Apr 24
Wk 12: Single-drone full stack (3.1)
Wk 13: 2-drone swarm full system (3.2)
Wk 13: Sensor readings during motion (3.3)
Wk 13: E-STOP verified < 2 sec (3.4)
Wk 13: Starlink loss → auto HOLD (3.5)
Wk 14: Single-drone pool test (4.1)
Wk 15: Multi-drone pool test (4.2)
Wk 15: Full mission validation (4.3)
90 Days
Apr 24 – May 7
Wk 16: Manual & documentation
Wk 16: Design Day preparation
Wk 17: Final report submission
Performance optimization
Integration test reports finalized
Notes: TALKING POINTS: - 30 Days: Focus on Phase 0-2 — interface specs, stub testing, pair integration - THIS WEEK: All interface specs agreed — IF-1 through IF-5 - Week 8: Stub testing — ESP32 sends MAVLink, reads sensors, talks to Jetson - Week 10: CRITICAL — Swarm↔Pixhawk pair test with Robert - Week 11: End-to-end command chain verified - 60 Days: Phase 3-4 — Full system and pool testing - Single-drone full stack, then 2-drone swarm - E-STOP verified, Starlink loss graceful degradation - Pool testing: single then multi-drone missions - 90 Days: Finalize — documentation, Design Day, final report - Task numbers (e.g., 1.1, 2.1) reference Integration Plan directly TIME: 45 seconds

## Slide 10
Risk Assessment & Mitigation
From Software Integration Plan — Risk Register (Section 8)
THE UNIVERSITY OF ARIZONA
9
AQUABOTS | ISR – Communications System
Risk | Prob | Impact | Mitigation | Owner
R1: MAVLink format mismatch ESP32↔Pixhawk | Med | High | Spec in Phase 0; logic analyzer in Phase 1 | John+Robert
R2: Starlink latency too high for control | Low | Med | Critical control via ESP-NOW; Starlink for telemetry | Mayra+John
R3: Sensor noise during motor vibration | Med | Med | Test during operation Phase 3; add filtering | Jamie
R5: UART port contention on ESP32 | Med | Med | UART0=console, 1=Pixhawk, 2=Jetson; verify early | John
R6: Spring Break schedule slip | High | Med | Front-load Phase 1 critical tasks to Week 8 | ALL
R7: Waterproofing failure | Med | High | Bench-test all integration before pool; conformal coat | ALL
R8: Pixhawk firmware incompatibility | Low | High | Verify firmware + MAVLink v2 in Phase 0 | Robert
Completed Mitigations
IF-6 protocol reliability: 0% packet loss verified
Auto-discovery, leader election, thread safety: all verified
Highest Priority
R1: MAVLink mismatch — spec due Feb 26
R6: Spring Break — front-loading Week 8 work
Notes: TALKING POINTS: - Risks pulled directly from Software Integration Plan Section 8 - R1 (MAVLink mismatch) is highest priority — on critical path - Mitigation: formal spec document due Feb 26, logic analyzer verification in Phase 1 - R5 (UART contention) is my responsibility — already planned allocation - R6 (Spring Break slip) mitigated by front-loading Phase 1 tasks to Week 8 - IF-6 risks already mitigated — proven 0% packet loss, working auto-discovery - R7 (waterproofing) — all integration bench-tested before going to pool TIME: 45 seconds